## Sheet1
Team Name: Loop Solutions Inc. |  |  | Project Name: Self-Start Physiotherapy
Responsibility Matrix |  |  |  |  | P: Primary S: Support
Task_ID | Task | Samuel Mallabone | Andrew Black | Jak Terpak | Craig Cook | Robert Northmore | Stephanie Pereira
Semester 1
1.1 | SRS - Section 1.1 |  |  | P
1.1 | SRS - Section 1.2 |  |  | P |  |  |  | Work Done as a team
1.1 | SRS - Section 1.3 | P | P | S | S | S | S
1.1 | SRS - Section 1.4 | P | P | S | S | S | S
1.1 | SRS - Section 1.5 |  |  | P
1.2 | SRS - Section 2.1 | P | P
1.2 | SRS - Section 2.2 | P | P
1.3 | SRS - Section 3.1 | P | P
1.3 | SRS - Section 3.2 |  |  | P
1.3 | SRS - Section 3.3 | [5 empty] | P
1.3 | SRS - Section 3.4 | [5 empty] | P
1.3 | SRS - Section 3.5 | [5 empty] | P
1.3 | SRS - Section 3.6 |  |  |  | P
1.3 | SRS - Section 3.7 |  |  |  | P
1.3 | SRS - Section 3.8 |  |  |  | P
1.3 | SRS - Section 3.9 |  |  |  | P
1.3 | SRS - Section 3.10 |  |  |  |  | P
1.3 | SRS - Section 3.11 | P | P
1.3 | SRS - Section 3.12 | P | P
2.1 | Workbook - Potential Entity Classes | S | P | P | S | S | S
2.2 | Workbook - Entity Class Attributes | P | P | S | S | P | S
2.3 | Workbook - Class Diagram | P | S | P | P | S | S
2.4 | FEAT-UC and UC-EntityClass | P | P | P | S | S | P
Semester 2
1.1 | Created 3 Routes |  | P
1.1 | Revised Schemas |  | P
1.1 | Revision explanation |  | P
1.2 | Created 5 tables | P
1.2 | Added 2 routes | P
1.2 | Revision explanation | P
1.3 | Added 2 routes |  |  |  |  | P
1.3 | Configured .gitignore |  |  |  |  | P
1.4 | Created 5 tables | [5 empty] | P
1.4 | Edited SDS document
1.5 | Created 5 tables |  |  | P
1.5 | Wrote technical decision SDS section |  |  | P
1.6 | Created 4 tables |  |  |  | P
1.6 | Revised all routes |  |  |  | P
2.1 | Manage Dynamic Forms Questions |  |  |  | P | P
2.2 | Manage Rehabilitation Plans |  |  | P |  |  | P
2.3 | Manage Exercises |  | P
2.4 | Manage Patient Profiles | P
3.1 | Create New Client | P
3.2 | Email Verification | P
3.3 | Upload Images |  | P
3.4 | Book Appointment |  | P |  | P
3.5 | Fill-In Injury Form |  |  |  |  | P
3.6 | Manage User Accounts |  |  | P |  |  | P
3.7 | Created Template For Scheduler |  |  |  |  | P
4.1 | Complete Assessment Test | P
4.2 | Added Encryption Service for Delicate Information | P
4.3 | Manage Test Assessments |  |  | P
4.4 | Manage Findings and Outcomes |  |  | P
4.5 | Assign Patient Plan |  | P
4.6 | Complete Exercises |  | P
4.7 | Finished the Scheduler |  |  |  |  | P
4.8 | Landing Pages - Home, About, etc.. |  |  |  | P
4.9 | Landing Pages - Physiotherapist, Admin | [5 empty] | P
5.1 | All Landing Pages |  |  |  | P
5.2 | Physio Calendar | [5 empty] | P
5.3 | Scheduler |  |  |  |  | P
5.4 | Reconstructed Assessment Tests |  |  | P
5.5 | Reconfigured Complete Assessment Test |  |  | P
5.6 | Dashboards |  | P
5.7 | Make Payment |  | P
5.8 | Generate Patient Report and Visualize Treatment Results | P | P
5.9 | Authenticate User | P
5.11 | (task ID is actually 5.10) Change Password | P